## Change Log Template
Change Log Template
Project Name: |  | PROG POE PART 2
Project Manager Name: |  | Aaron Fourie
Program Manager Name: |  | Mr Henly
Change No. | Type | Description | Date Identified | Priority | Date Work Begins | Date Work Resolved
1 | Added | Register window | 2022-11-10 | High | 2022-11-10 | 2022-11-10
2 | Added | Register functonality | 2022-11-11 | High | 2022-11-11 | 2022/22/11
3 | Added | Create Database StudentData | 2022-11-12 | High | 2022-11-12 | 2022-11-12
4 | Fixed | INSERT INTO errors | 2022-11-12 | Critical | 2022-11-12 | 2022-11-12
5 | Added | Created database | 2022-11-14 | Critical | 2022-11-14 | 2022-11-14
6 | Added | Created tables | 2022-11-14 | Critical | 2022-11-14 | 2022-11-14
7 | Added | Created LoggedInViewModules.cs | 2022-11-15 | Medium | 2022-11-15 | 2022-11-15
8 | Added | Created LoggedInStudyProgress.cs | 2022-11-15 | Medium | 2022-11-15 | 2022-11-15
9 | Fixed | SELECT FROM Errors | 2022-11-24 | Medium | 2022-11-24 | 2022-11-24
10 | Added | Created ADO.NET Entity framework layer | 2022-11-16 | Medium | 2022-11-17 | 2022-11-24
11 | Added | DBConnection.cs class with Connection string | 2022-11-15 | Critical | 2022-11-15 | 2022-11-15
12 | Update | Readme File | 2022-11-26 | Low | 2022-11-26 | 2022-11-26
13 | Added | Changelog | 2022-11-27 | Low | 2022-11-27 | 2022-11-26
14 | Added | Register Video | 2022-11-25 | High | 2022-11-25 | 2022-11-28
15 | Added | Login Video | 2022-11-25 | High | 2022-11-25 | 2022-11-28

## How to Use Change Log Template
How to Use Our Change Log Template
After you open up the change log template, you’ll see that there are many column headings with blank fields beneath them. These blank cells are for you to input the related data. Of course, the whole change management log template is editable, so feel free to change headings to match your work process and nomenclature.
Definition of Terms
Project Name: Here is where you name the project you’re working on, as there might be several projects in a program ongoing simultaneously.
Project Manager Name: Note the person leading the project, feel free to add contact info.
Program Manager Name: If the project is part of a larger program, then state the name of the person managing that with contact info
Change No.: Simply a numerical list of the changes collected on this spreadsheet in order to make tracking easier.
Date Identified: When the change is first noticed, this field captures that date.
Description: Describe in brief what the change is.
Status: Note the current status of the change, whether it’s open, meaning identified but not yet addressed, work in progress, when you’ve started to execute the steps to resolve the change or closed when it’s done. This column can also capture if the change is late, on hold or combined, such as when two similar change requests are merged. This is a dropdown menu.
Priority: Note how important it is to address the change, critical, high, medium or low. This is a dropdown menu.
Assigned: This is the person who has been tasked with resolving the change request.
Expected Resolution: Note when the change request should be resolved.
Action: Here you list the steps that need to be taken to resolve the change request.
Impact: Note how the change is impacting the project, such as on the schedule, scope, resources, etc.
Date Work Begins: When did the work on resolving the change request begin?
Escalation Required: If there is a need to bring in further resources to resolve the change order.
Date Work Resolved: What is the date when the issue request was resolved and closed?
Signoff: The manager overseeing this change request signs off on its successful completion here.
Comments: If there are any additional notes that don’t fit elsewhere on the spreadsheet they should go here.